## Sheet1
Week | PM (Project Manager) Ulugbekov Almazbek | FD (Frontend Developer) Osmonov Ulugbek | BD (Backend Developer) Sultanov Temirlan | UI/UX (Designer) Talantbekov Tilek
Week 1 | Finalize project scope, objectives, and deliverables. Set up tools. | Set up basic HTML/CSS structure for the browser UI. | Set up Python environment, install libraries (PyQt5). | Research and create wireframes for the browser interface.
Week 2 | Plan project milestones, set up project management tools (Jira, Trello). | Build the main window of the browser using PyQt5. | Set up the backend logic for browsing (e.g., URL loading, navigation). | Finalize the layout, colors, and design elements for the UI.
Week 3 | Ensure communication between teams, track progress. | Implement navigation buttons (back, forward, reload). | Work on backend interactions (e.g., handling search queries). | Conduct user testing on wireframes and UI designs.
Week 4 | Organize weekly sprint reviews and check-ins. | Finalize UI (integrating HTML with PyQt5, styling buttons, etc.). | Add features to the backend (e.g., handle error pages, history). | Finalize UI/UX design based on feedback and usability testing.
Week 5 | Track project completion and prepare for testing. Plan deployment. | Test the browser UI on different screen sizes, ensure responsiveness. | Test backend features, ensure proper error handling. | Review and finalize visual design, icons, and loading screens.
Week 6 | Finalize documentation, deployment plan, and user guide. | Final UI and feature testing, fix bugs, prepare for deployment. | Finalize backend, ensure security, and prepare for deployment. | Ensure design consistency across the app, finalize the look and feel.